## Project Plan
Event Name | Spring conference GBS for the Next Decade |  |  | Code | m_EVENT39
Section | Task | Comments | Responsible | Start date | Finish date | Status [%]
Konferencja
Data | Wybranie daty | 13 pażdziernika 2026 | Krystian, Michał |  |  | 100
Miejsce | Potwierdzenie venue | Stare Kino Events - Industria by Stare Kino - Ogrody Geyera Piotrkowska 293/305 | Edyta |  |  | 100
| Wycena/Kosztorys |  | Edyta |  |  | 75
| Zorganizowanie Sceny, wycena |  | Stare Kino |  |  | 50
| Call z organizatorem sceny |  |  |  |  | 0
| Zorganizowanie Krzeseł na konferencje | w żadnej wypożyczalni w Łodzi nie ma krzeseł z podłokietnikami - koszt sprowadzenia krzeseł z Wwa genereuje dodatkowy koszt transporty rzędu 2-3 K plus krzesła. Krzesła wyściełane ze starego kina ( zdjęcie obok) całkowity koszt wypożyczenia 1000 zł | Edyta |  |  | 75
100
Agenda | Draft agendy | w zakładce drugiej | Robert |  |  | 100
| Potwierdzenie finalnej wersji |  | Krystian |  |  | 50
Speakerzy | Wyznaczenie panelistów |  | Michał, Robert, Paweł, Tom |  |  | 50
| Wysłanie zaproszeń do panelistów |  | Michał, Robert, Paweł, Tom |  |  | 25
| Potwierdzenie Udziału |  | Michał, Robert, Paweł, Tom |  |  | 0
| Pozyskanie materiałów marketingowych (zdjęcie, bio, logo) od speakerów |  | Edyta |  |  | 0
Prezentacje | Pozyskanie inputu do prezentacji speakerów na panele |  | Michał, Robert, Paweł, Tom |  |  | 0
| organizacja i dry run z panelistami przed eventem (scenariusz panelu dyskysyjnego) |  | Michał, Robert, Paweł, Tom |  |  | 0
Catering | Potwierdzenie dostawcy - Stare Kino |  | Edyta |  |  | 100
| Wycena/Kosztorys |  | Edyta |  |  | 100
| Wycena alkoholi - na stoły ( wódka, whiskey) | wódka + whiskey( Stare Kino ) - 85 zł / osobę netto | Edyta
| Zorganizowanie drinków - stacja z barów | Stare Kino w ofercie proponuje tylko mocne alkohole i wino stojące na stole - drinki robione samodzielnie. Jeśli oferta miałaby obejmować drinki przygotowywane przez barmana - trzeba dopłacić 4000 netto |  |  |  | 25
| Zorganizowanie Jorgiego plus wycena | Cześć konferencyjna z winem - 7000 netto | Edyta |  |  | 0
| Jorgie wino wieczór - bez obsługi wycena | sama obsługa 2000 netto | Edyta
Goście | zbieranie potwierdzonych gości na listę - ongoing process |  | Edyta |  |  | 0
Wideorelacja - własna | Zorganizowanie sprzętu |  |  |  |  | 0
| Ustalenie planu/pomysłów na wideo promocyjne | może Karolina? |  |  |  | 0
| Filmowanie na miejscu | Wideo promocyjne, Lista osób, relacja z miejsca |  |  |  | 0
Fotorelacja - zewnętrzna | Zorganizowanie sprzętu |  |  |  |  | 0
| Fotograf/wycena | Czy zewnętrzny fotograf ? |  |  |  | 0
| Ustalenie planu/pomysłów na zdjęcia |  |  |  |  | 0
Fotorelacja własna | Zdjęcia na miejscu |  | Edyta |  |  | 0
Podsumowanie eventu | Wyzanczenie osoby do notowania contentu paneli | PM? |  |  |  | 0
| Stworzenie podsumowania |  |  |  |  | 0
Gadżety | Organizacja produktu: Smyczki i badge |  | Edyta |  |  | 0
| Organizacja produktu: Bransoletki/opaski | do zastanowienie czy potrzebne | Edyta |  |  | 0
| Dostarczenie na miejsce |  |  |  |  | 0
Muzyka - oprawa dj kolacja | Ustalenie muzyki na konferencje - człowiek od nagłośnienia, jingle w przerwie, itp. |  |  |  |  | 0
| Muzyka na lunch/coffee break? Jw. |  |  |  |  | 0
Komunikacja & Visuals
EVENEA | Stworzenie Evenei dla wydarzenia | TRUE | Natalia |  |  | 100
Plan komunikacji | Wyznaczyć daty wysyłania | FALSE | Edyta |  |  | 100
| Przygotowanie agendy eventu własnego w grafice/mailingu (IFA) | FALSE | Natalia |  |  | 100
| Przygotowanie pakietu komunikacyjnego nr 1 (temat, datam miejsce) | FALSE | Edyta |  |  | 100
| Pakiet komunikacyjny nr 2 (agenda, tekst przewodni) |  | Edyta |  |  | 100
0
0
Zaproszenia | SAVE the Date draft |  | Natalia |  |  | 100
| Zaproszenie draft |  | Natalia |  |  | 100
| Zaproszenie/SAVE the DATE zaakceptowane |  | Robert, Edyta |  |  | 100
| Wybranie listy gości | C-level, budget decisive people | Michał, Robert |  |  | 100
| przygotowanie mailingu w toolu lub do wysyłki z macro |  | Robert, Edyta |  |  | 100
| wysyłka mailingu |  |  |  |  | 100
| Przygotowanie i wysyłka mailingu w Get Response |  |  |  |  | 100
| wysłanie komunikacji do SEALS celem informacji o evencie (zaproszenie to forward) |  | Edyta |  |  | 100
0
Grafiki na social media | przygotowanie scenariusza nagrywki zaproszenia/filmu promo przed eventem |  | Edyta |  |  | 100
| przygotowanie nagrywki zaproszenia/filmu promo przed eventem |  |  |  |  | 25
| publikacja filmu (zadanie other, w planie komunikacyjnym) |  |  |  |  | 25
Opis wydarzenia | Stworzenie tekstu przewodniego x2 |  | Edyta, Natalia |  |  | 50
| Baza osób do wysyłki | C-level, budget decisive people | Krystian, Michał, Robert |  |  | 100
| Rozsyłka do ludzi |  |  |  |  | 0
Materiały drukowane/branding | Stworzenie draftu materiałów |  | Edyta |  |  | 0
| Finalna wersja zaakceptowana |  |  |  |  | 0
Grafika na panele przy diodzie | Stworzenie slajdów/grafiki na panele/roll upy wysokie |  |  |  |  | 0
| Finalna wersja zaakceptowana |  |  |  |  | 0
Materiały audio-wizualne na TV | Materiały promocyjne wideo na przed kolacją od sponsorów |  | ? |  |  | 0
Komunikacja po evencie | thank you email - do speakers- przygotowanie |  | Edyta |  |  | 0
| thank you email do speakers - wysyłka maila |  | Edyta |  |  | 0
| thank you emails to participants - przygotowanie np. baza Evenea, CRM) |  | Edyta |  |  | 0
| wpisanie osób/leadów do CRM |  | Edyta
| thank you emails to participants - wysyłka |  | Edyta |  |  | 0
Retro meeting do kalekdarza |  |  | Edyta
Kolacja
Miejsce | Potwierdzenie venue |  | Edyta |  |  | 100
Catering | Propozycja menu/wycena |  | Edyta |  |  | 100
| Potwierdzenie menu |  |  |  |  | 0
Sprzątanie | - |  |  |  |  | 0
Dekoracje na wejściu, ścianki | Zorganizowanie ścianki |  | Edyta |  |  | 0
bannery na wejściu mocowane do konstrukcji zadaszenia | Transport ścianki |  |  |  |  | 0
0
Muzyka - oprawa dj | Ustalenie muzyki |  |  |  |  | 0
| Koordynacja z DJ |  | Paulina
25
Ogólne
Umowy/sponsorships | Umowa z miastem potwierdzona i podpisana | Potwierdzenie pakietu sponsor + Umowa o recharge | Edyta |  |  | 100
| Rozliczenie po evencie - dokumenty i fotovideorelacja |  | Edyta
| Umowa z venue potwierdzona i podpisana |  | Paulina |  |  | 25
| Umowa z C&W plus kosztywystawienie fv | Potwierdzenie pakietu sponsporskiego + umowa | Edyta |  |  | 0
Umowa z DJ czy firmą oświetleniową/nagłośnieniową
Ubezpieczenie uczestników imprezy | Podpisanie ubezpieczenia (polisy) z Olą |  | Ola Stablewska |  |  | 0
Ochrona | n/a
Parking | Parking dla gości - potwierdzenie ilości i zapłata | Parking płatny, można wynająć 30 zł za auto na 24 h, parking podlega pod APCOA. |  |  |  | 0
Hotel | uzyskanie od organizatorów zniżek na zakwaterowanie (IFA) | Hotel Puro - 30 % zniżna do końca 2027 na Łódź na stronie rezerwacyjnej na hasło Adaptive |  |  |  | 0
Faktury/pro forma | Wysłanie faktury do zapłaty za catering/restaurację do Admina |  |  |  |  | 0
| pozyskanie faktury za materiały i gadżety i wysłanie do Admin do zapłaty |  |  |  |  | 0
| Zapłata za materiały i gadżety, wysłanie potwierdzenia płatności do Admin |  | Ola |  |  | 0
| uzyskanie od organizatorów mapek stoisk/przestrzeni w restauracji |  | Edyta |  |  | 0
25
1
Support na Recepcji (Adaptive) | [5 empty] | 1
Recepcja - stolik, wydawanie badge, meble, rozstawienie | z p. Dariuszem
stolik koktajlowy
Montaż demontaż sceny w salkach
Aktualizacja listy gości - mailingu z CRM nowy mailing

## Agenda draft
Start | End | Event
Panellists
|  | Topics in agenda | Comments | Name | Surname | Company | Contact Person | Attendance confirmed?
10:30 | 11:00 | Registration & Welcome Coffee | [5 empty] | FALSE
11:00 | 12:30 | Pre conference workshop: Make AI Work! - Interactive AI Agent Lab |  | Robert | Paweł | Adaptive |  | FALSE
12:30 | 13:30 | Networking Lunch | [5 empty] | FALSE
13:30 | 14:00 | Official Welcome | Intro plus 15 min- Krystian - benchmarks, current state, trends, touching 4 areas | Krystian | Bestry | Adaptive |  | FALSE
14:00 | 14:45 | Shape the Future! - GBS Reinvention for the Digital Era | 1/4 areas drive by THOMAS | Tom | Dobis | Adaptive | MiBi | FALSE
|  |  |  | Krystian | Bestry | Adaptive |  | FALSE
|  |  |  | Agnieszka | Belowska | Nordea | agnieszka.belowska@nordea.com | TRUE
[7 empty] | MiBi | FALSE | Michał Wierzbowski
14:45 | 15:30 | Stay in Command! - Enterprise Transformation Management Office as the Engine of Large-Scale Change | 2/4 areas drive by Paweł | Paweł | Płocki | Adaptive |  | TRUE
|  |  |  | Mariusz | Pietrzak | Elekta |  | TRUE
|  |  |  | Tomasz | Leśniewski | Olympus | Paweł to chase | FALSE
15:30 | 16:00 | Coffee Break | [5 empty] | FALSE
16:00 | 16:45 | Own the Journey! - From Process Redesign to Digital Delivery | 3/4 areas drive by Robert | Robert | Godziszewski | Adaptive |  | FALSE
|  |  |  | Marzena | Kardas | Barry Callebaut | confirmed | TRUE
|  |  |  | Arnaud | Diaz | PPG | confirmed | TRUE
FALSE
16:45 | 17:30 | Win the Hearts! - Building GBS Capabilities for Business related processes (second runner: Human-Centered Change in Digital Transformation) | Speakers/Miasto/HR by MiBi | Michał | Bielawski | Adaptive |  | FALSE
|  |  |  | Łukasz | Wielochowski | Moderna |  | TRUE
|  |  |  | Dariusz | Adamus | Takeda |  | FALSE
|  |  |  | Mateusz | Sipa | Invet in Lodz |  | TRUE
17:30 | 18:00 | Wrap-Up/Key take-aways for the next decade | We need to catchh take aways for the future/not summary/agree wirh Wiktor what's the purpose of this wrap up by Wiktor Doktór | Witktor | Doktór | ProProgressio |  | FALSE
18:00 | 18:30 | Afternoon Exchange & Adaptive Wine Talks | [5 empty] | FALSE
18:30 | 0:00 | Seated networking dinner | [5 empty] | FALSE

## Agenda 13.10 UMŁ
|  | Topics in agenda | Name | Surname | Company
10:30 | 11:00 | Registration & Welcome Coffee
11:00 | 12:30 | Pre conference workshop: Make AI Work! - Interactive AI Agent Lab | Robert | Paweł
12:30 | 13:30 | Networking Lunch
13:30 | 14:00 | Official Welcome
14:00 | 14:45 | Shape the Future! - GBS Reinvention for the Digital Era | Tom | Dobis
|  |  | Krystian | Bestry
|  |  | Agnieszka | Belowska | Nordea
14:45 | 15:30 | Stay in Command! - Enterprise Transformation Management Office as the Engine of Large-Scale Change
|  |  | Mariusz | Pietrzak | Elekta
|  |  | Tomasz | Leśniewski | Olympus
15:30 | 16:00 | Coffee Break
16:00 | 16:45 | Own the Journey! - From Process Redesign to Digital Delivery | Robert | Godziszewski
|  |  | Marzena | Kardas | Barry Callebaut
|  |  | Arnaud | Diaz | PPG
16:45 | 17:30 | Win the Hearts! - Building GBS Capabilities for Business related processes (second runner: Human-Centered Change in Digital Transformation) | Michał | Bielawski
|  |  | Łukasz | Wielochowski | Moderna
|  |  | Dariusz | Adamus | Takeda
|  |  | Mateusz | Sipa | City
17:30 | 18:00 | Wrap-Up/Key take-aways for the next decade
18:00 | 18:30 | Afternoon Exchange & Adaptive Wine Talks
18:30 | 0:00 | Seated networking dinner

## actions
🕚 Event Agenda (may change):
10:30 - 11:00 📋 Registration & Networking
11:00 - 12:30 🤖 Make AI Work! - Interactive AI Agent Lab
12:30 - 13:30 🍽 Lunch
13:30 - 14:00 👋 Official Welcome
14:00 - 14:45 🌐 Shape the Future! - GBS Reinvention for the Digital Era
14:45 - 15:30 🏢 Stay in Command! - Enterprise Transformation Management Office as the Engine of Large-Scale Change
15:30 - 16:00 ☕ Coffee Break
16:00 - 16:45 🔄 Own the Journey! - From Process Redesign to Digital Delivery
16:45 - 17:30 🔀 Win the Hearts! - Human-Centered Change in Digital Transformation
17:30 - 18:30 🏁 Wrap-Up
18:30 - 19:00 🤝 Sponsors' Break
19:00 - 00:00 🍷 Dinner & Networking
2026-09-17
Liberty Motors - Edyta sponsoring |  |  | telefon
oferta hotele Puro & Stare Kino |  | Puro | Edyta | ew. Paula | FILIP DRÓŻDŻ | Hubert | Terela | General Manager
Zniżka korpooracyjna na całą sieć Puro |  |  | Stare Kino - Dariusz |  | Sales Manager
puro - Edyta
Komunikacja logistyka mail do zarejestrowanych |  |  |  | Edyta | mob.: +48 782 677 778
Parking - doprezycować | komunikacja |  |  |  | tel.: +48 42 715 90 23
Jorge - data eventu | 2026-10-13 | Zatowarowanie |  | Edyta
spotkanie z Dariuszem i oświetleniowcem - next week |  |  |  | Edyta | plus Karolina Matejko
Scenotechnika - biuro@kacprzakestrada.pl, 604-454-269 Albert

## Agenda with key words
Start | End | Event
Panellists
|  | Topics in agenda | Content/Areas/Key words | Comments | Name | Surname | Company | Contact Person | Attendance confirmed?
10:30 | 11:00 | Registration & Networking (plus coffee break) | [6 empty] | FALSE
11:00 | 12:30 | Pre conference workshop: Make AI Work! - Interactive AI Agent Lab | Make AI Work! – instead of slides about AI, let's simply build it. An interactive session opening the conference: in teams, participants create their own AI agent and check live whether it actually works. No theory, no tool selling – just a real use case, a keyboard and a result you can see straight away. Keywords: AI in practice, live demo, teamwork, networking, inspiration to start the day. |  | Robert | Paweł |  |  | FALSE
|  | Coffee Break - customer services | Coffee sponsor – coffee machine at the customer service company's stand; people stay there for 3 hours; possible hands-on testing of their tool over coffee (Michał) | [5 empty] | FALSE
11:00 | 11:45 | HR - skills for the future -Business & City (45 min) | Michał: do NOT run a separate session for the city and HR here – they should join the last content session together (Win the Hearts). He does not want a session about location. | [5 empty] | FALSE
11:45 | 12:30 | tbc - tech sponsors' presentation (45 min) |  |  | Łukasz | Olechnowicz |  |  | FALSE
12:30 | 13:30 | Lunch | [6 empty] | FALSE
13:30 | 14:00 | Welcome Krystian/Pustelnik - official |  | Intro plus 15 min- Krystian - benchmarks, current state, trends, touching 4 areas |  |  |  |  | FALSE
14:00 | 14:45 | Shape the Future! - GBS Reinvention for the Digital Era | Blocks start with strategic topics: GBS Reinvention = strategy. Each part opens with a short mini-speech by the host (what the world / the leaders are saying). What should GBS focus on right now? • What the market says, what the leaders do – 2-3 opening slides with trends and figures (reports, benchmarks, future expectations) • Strategy = the answer to a trend – this block says WHAT the trend is; concrete process solutions come in the following sessions • Real organisations instead of theory – logo + 2 sentences: who is growing their R&D, who moved processes to India, who went for robotics/automation • Technology flips the table – new technology does not improve the process, it redefines it; what is fully automated today • Take-away for the future – 5 min wrap-up: which trend GBS has to buy into right now (input for Wiktor's wrap-up) | - 15 min trends/benchmark z Adaptive - 30 min dyskusja z innymi MAIN POINTS: - jak technologia drive'uje process - przy nowej technoligii ona wywraca stolik że coś jest teraz w pełni zautomatyzowane | Tom | Dobis |  | MiBi | FALSE
[5 empty] | Agnieszka | Belowska | Nordea | agnieszka.belowska@nordea.com | TRUE
[5 empty] | Rafał | Tylek | Rolls-Royce | ? Tbc if here | FALSE
14:45 | 15:30 | Stay in Command! - Enterprise Transformation Management Office as the Engine of Large-Scale Change | Transformation Management Office: how to do it and how to implement it so that the transformation succeeds. Speaker: Paweł (Michał moves to the last session). • From strategy to execution – the strategy is already on the table; this block answers HOW to implement it so the transformation succeeds • ETMO as the engine of change – who holds the wheel in large-scale transformation: structure, governance, decision-making, ownership • What the market says – 1-2 opening slides: how leaders run transformations and why some of them fail • Real-life examples instead of methodology – actual implementations: what worked, what broke down, what was missing along the way • Take-away for the future – 5 min wrap-up: what GBS transformation cannot succeed without (input for Wiktor's wrap-up) | Paweł | Justyna | Kierska | Barry Callebaut |  | TRUE
[5 empty] | Kasia | Zalewska | Bruker |  | TRUE
15:30 | 16:00 | Coffee Break | [6 empty] | FALSE
16:00 | 16:45 | Own the Journey! - From Process Redesign to Digital Delivery | Now that we have implemented the transformation – how do we deliver digital delivery. • Transformation already implemented – what next? This block goes deepest into specifics: how to genuinely deliver digital delivery day to day • Process redesign, not process digitisation – from redesigning the process to delivering the service digitally, rather than putting the old process onto a new tool • What the market says – 1-2 opening slides: how leaders set up service delivery today and where the automation boundary is moving • Concrete tools and solutions – how companies really automated things: what they equipped themselves with, what optimises their processes and service delivery • Take-away for the future – 5 min wrap-up: what GBS can implement at home straight away (input for Wiktor's wrap-up) | Robert tutaj bardziej w kierunku tego jak rzeczywiście zautomatyzowali tematy albo jak obłozyli się toolami i rozwiązaniami które im optymalizują procesy i service delivery | Arnaud | Diaz | PPG | Robert | FALSE
[7 empty] | Robert to confirm |  | FALSE
[5 empty] | Lan | QuanVan | Trumpf | to confirm by Paweł by 23.09 EOB | FALSE
FALSE
16:45 | 17:30 | Win the Hearts! - Building GBS Capabilities for Business related processes (second runner: Human-Centered Change in Digital Transformation) | Skills / building GBS capabilities for the business and those functions (incl. pharma). A solid content-led introduction: which processes, how new functions are being implemented. Room for the HR partner (developing people and talent) and for the city (an ecosystem supporting growth). A question to the market: do you have the talent to run these processes – otherwise we will place them here. • The technology is already there – but who will do the work? Closing the narrative: strategy, transformation and delivery go nowhere without people and capabilities • Building GBS capabilities for the business – business processes and new functions (incl. pharma): which processes are coming and how they are implemented • A question to the market – do you have the talent to run these processes? Because we have no problem placing them here • HR and the city at one table – the HR partner develops people and talent, the city builds an ecosystem supporting the sector's growth (no location topics) • Take-away for the future – 5 min wrap-up: which capabilities GBS needs for the next decade (input for Wiktor's wrap-up) | Speakers/Miasto/HR |  |  |  |  | FALSE
[5 empty] | Łukasz | Wielochowski | Moderna |  | TRUE
[5 empty] | Dariusz | Adamus (?) | Takeda | Lady from R&D, MiBi to confirm | FALSE
[5 empty] | Mateusz | Sipa | City |  | TRUE
17:30 | 18:00 | Wrap-Up/Key take-aways for the next decade | Wiktor w agendzie jako spiker, nie tylko wzmianka - podsumowanie 'for the next decade'. Michał: ok. 25 min, ma być podsumowanie, nie luźne rozgadanie. | Wyłapanie take aways for the future niż summary, ustalić z Wiktorem do czego dążymy. |  |  |  |  | FALSE
18:00 | 18:30 | Travel/ Bifor/ Promo | [6 empty] | FALSE
18:30 | 0:00 | Networking & Dinner | [6 empty] | FALSE
|  | Lan Quan Van |  |  | ACTIONS 13.08.2026
|  | Elisabeth Ploquuin | Schneider Electric Transformation & Excellence Manager |  | Doprosić Toma do spotkań GBS Next Decade
|  | Radek Kobrzak |  |  | Odezwac się do Kierskiej - MIBI - podesłac Michałow temat żeby miał ;)

## Parking lot
Nr. | Pomysł/Pytanie/ Temat | Osoba zgłaszająca | Data zgłoszenia | Priorytet | Status | Właściciel | Komentarz
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Agenda (hidden)
Start | End | Event |  |  | Paneliści
9:00 | 9:30 | Registration & Networking (plus coffee break)
|  |  | Owner/Prowadzący | Kontent/tematy/obszary | Imię | Nazwisko | Firma | Osoba kontaktująca się | Potwierdzona obecność? | Agenda do comms
9:30 | 11:00 | HR workshop? Sipa sesja talent pool, Schindler - w Łodzi announcement tbc, Talent/HR Lab. Upskill/Talent ecosystem for future | MiBi/Sipa | [5 empty] | FALSE
11:00 | 12:30 | Make AI Work! - Interactive AI Agent Lab/równolegle GBS Masters HR Talent Pool | Robert |  | Robert | Godziszewski |  |  | TRUE | Option 1 |  | Option 2
[5 empty] | Paweł | Płocki |  |  | TRUE | 11:00 | Interactive AI session | 11:00 | Interactive AI session
[5 empty] | Łukasz | Olechnowicz |  |  | FALSE
12:30 | 13:30 | Lunch | [6 empty] | FALSE | 12:30 | Lunch | 12:30 | Lunch
13:30 | 14:00 | Welcome Krystian/Pustelnik | Krystian/ Aleksandra Szyłło? | [5 empty] | FALSE | 13:30 | Official Welcome | 13:30 | Official Welcome
14:00 | 14:45 | Shape the Future! - GBS Reinvention for the Digital Era |  | - 15 min trends/benchmark z Adaptive - 30 min dyskusja z innymi MAIN POINTS: - | Tom | Dobis |  | MiBi | TRUE | 14:00 | Module 1: Mine your Future! - Digital Reinvention | 14:00 | Focus Area 1: Mine your Future! - Digital Reinvention
[5 empty] | Agnieszka | Belowska |  |  | FALSE | 14:45 | Module 2: Drive Efficiency! - Closing the Gap Between Investment and Impact | 14:45 | Focus Area 2: Drive Efficiency! - Closing the Gap Between Investment and Impact
FALSE
14:45 | 15:30 | Stay in Command! - Enterprise Transformation Management Office as the Engine of Large-Scale Change | Michał |  | Justyna | Kierska |  |  | TRUE | 15:30 | Coffee & Networking Break | 15:30 | Coffee & Networking Break
[9 empty] | FALSE | 16:00 | Module 3: Technology Led Innovation! - E2E AI-Driven Transformation | 16:00 | Focus Area 3: Technology Led Innovation! - E2E Digital Transformation
15:30 | 16:00 | Coffee Break | [6 empty] | FALSE | 17:30 | Wrap-Up | 17:30 | Wrap-Up
16:00 | 16:45 | Own the Journey! - From Process Redesign to Digital Delivery | Robert | tutaj bardziej w kierunku tego jak rzeczywiście zautomatyzowali tematy albo jak obłozyli się toolami i rozwiązaniami które im optymalizują procesy i service delivery | Kamila | Szewczyk | Alcon | Robert | TRUE | 18:30 | Sponsors Break | 18:30 | Sponsors Break
[5 empty] | Lan | QuanVan | Trumpf |  | FALSE
FALSE
16:45 | 17:30 | Win the Hearts! - Building GBS Capabilities for Business related processes (second runner: Human-Centered Change in Digital Transformation) |  |  | Maciej | Kulbat (?) | Astellas Pharma |  | FALSE | 19:00 | Dinner & Networking | 19:00 | Dinner & Networking
[5 empty] | Łukasz | Wielochowski | Moderna |  | FALSE
[5 empty] | Dariusz | Adamus (?) | Takeda |  | FALSE
FALSE
17:30 | 18:30 | Wrap-Up | Wiktor Doktór | [5 empty] | FALSE
18:30 | 19:00 | Travel/ Bifor/ Promo | [6 empty] | FALSE
19:00 | 0:00 | Networking & Dinner | [6 empty] | FALSE
|  | Lan Quan Van | TRUMPF |  | ACTIONS 13.08.2026
|  | Elisabeth Polquin | Schneider Electric |  | Doprosić Toma do spotkań GBS Next Decade
|  | Radek Kobrzak | Schneider Electric |  | Odezwac się do Kierskiej - MIBI - podesłac Michałow temat żeby miał ;)